# Software Development Cost Estimate: Study Group Finder Web App

## 1. Project Scope & Goal

Goal: To create a secure, responsive web application that allows university students to easily create, search for, and join study groups for specific courses, moving away from unorganized chat apps and bulletin boards.

Technology Stack (Assumed):

- Frontend: React (with Tailwind CSS for rapid styling) in AWS on NGINX.

- Backend/Database: Serverless Architecture (e.g., Firebase/Firestore database) for rapid development and real-time updates (other example: Node.js backend in AWS).

## 2. Feature Breakdown and Complexity

The project requirements are categorized into key modules, along with their estimated complexity level.

| Module | Features (Requirements) | Complexity |
| --- | --- | --- |
| I. Authentication & Profiles | Student Registration, Login/Logout, Basic Profile Setup (Name, Course Load, University). | Medium |
| II. Study Group Creation | Form for creating a new group: Subject selection, Time/Day, Location (Library, Cafe), Online/Offline toggle, Max Group Size. | High |
| III. Search & Discovery | Comprehensive Search (by Subject/Course Code), Filtering (Time, Location, Online/Offline), Displaying Group Cards/List. | Medium |
| IV. Group Membership & Roster | Logic to Join/Leave Group, Displaying the list of members in a group, Basic member roles (Creator/Member). | Medium |
| V. Internal Communication | Simple text-based Announcements or basic group messaging for members only. | High |
| VI. Infrastructure & Deployment | Environment setup, Database configuration, Hosting/Scalability prep, Initial QA/Testing. | Medium |

## 3. Estimated Effort (Time)

This estimate provides a breakdown of technical hours required across various roles. This is based on a standard Agile development cycle (Planning, Development, Testing, Review).

| Role / Phase | Allocation | Estimated Hours |
| --- | --- | --- |
| Project Management & Planning | Scope definition, Sprints, Client communication | 80 |
| UX/UI Design & Prototyping | Wireframing, User flow mapping, Component styling | 60 |
| Frontend Development | Building responsive UI components, integrating with API, state management (Modules I, II, III, IV, V) | 280 |
| Backend/Database Development | Authentication setup, Database structure, API endpoints, Real-time data handling (Modules I, II, IV, V, VI) | 220 |
| Quality Assurance (QA) & Testing | Unit testing, Integration testing, User acceptance testing (UAT), Bug fixing | 120 |
| Deployment & Launch Prep | Final environment setup, Security review, App store/Hosting launch | 40 |
| TOTAL ESTIMATED EFFORT |  | 800 Hours |

## 4. Cost Calculation

Assuming a blended hourly rate of $95 USD (which accounts for a mix of senior and mid-level developers, designers, and project managers), the core cost is calculated as follows:

Total Estimated Effort x Blended Hourly Rate = Base Cost

800 Hours x $95/Hour = $76,000

### Final Estimated Cost Range

We must include a contingency budget for unforeseen technical challenges, scope creep, and extra testing.

| Cost Component | Cost |
| --- | --- |
| Base Development Cost | $76,000 |
| Contingency (20% of Base) | $15,200 |
| TOTAL ESTIMATE | $91,200 |

Development Project Cost Range (for budgeting purposes):

$80,000 - $105,000

Estimated Monthly Costs (Non-Development for budgeting purposes):

Backend & Frontend: AWS EC2 Instance [t3.large] $0.0832 * 24 hours a day * 31 days a month = $61.90 per month (running NGNIX, MYSQL, and Node.js)

Elastic IP: $0.005 per hour * 24 hours * 30 days = $3.6 per month

500 users (100 GB is free minus 100) at 1 GB out 400*.09 per GB = $36 per month data transfer out

Marketing Costs: $1000 per month

Other Costs:…..

Total Monthly Costs: $1101.50

Disclaimer: This estimate is based on the features defined in the project description and assumes a modern, efficient technology stack. Any significant addition to the scope (e.g., in-app video chat, payment processing, or deep integration with university APIs) would require a revised estimate.